## Sheet1
DATE | WORK DONE | START TIME | END TIME | TIME SPENT IN HOURS | SPRINT | TOTAL HOURS : | 195.7
2020-01-22 | CS 4360 lecture | 12:00 | 13:50 | 1.83 | SPRINT 1
2020-01-25 | Installed Android Studio | 17:30 | 17:40 | 0.16
2020-01-25 | Notified group of installing Android Studio & Enabled developer mode with USB debugging on personal Android phone | 17:50 | 18:31 | 0.68
2020-01-25 | Watched “Android Kotlin Beginner Tutorial” at https://www.youtube.com/watch?v=sZWMPYIkNd8 | 19:06 | 20:13 | 1.11
2020-01-27 | CS 4360 lecture | 12:00 | 13:50 | 1.83
2020-01-29 | CS 4360 lecture | 12:00 | 13:50 | 1.83
2020-01-29 | Assisted Darey Lee in writing up proposal | 14:00 | 16:00 | 2
2020-01-30 | Practiced creating Android app front end with Android Studio | 16:05 | 23:48 | 7.71
2020-02-03 | CS 4360 lecture | 12:00 | 13:50 | 1.83
2020-02-04 | Read documentation about how to use Kotlin at kotlinlang.org | 10:41 | 17:47 | 7.1
2020-01-27 | CS 4360 lecture | 12:00 | 12:30 | 0.5
2020-02-05 | Created itenerary page for Last Seen app with Darey Lee | 12:30 | 17:48 | 5.3
2020-02-07 | Put together Sprint 1 PowerPoint presentation | 19:50 | 2:24 | 6.4
2020-02-08 | Finished putting together Sprint 1 PowerPoint presentation | 15:08 | 21:18 | 6.16
2020-02-10 | CS 4360 lecture | 12:00 | 13:50 | 1.83 | SPRINT 2
2020-02-10 | Teem Meeting | 14:00 | 15:50 | 1.83
2020-02-12 | CS 4360 lecture | 12:00 | 13:00 | 1
2020-02-12 | Worked on getting Travis to work on the repository with Ron | 13:02 | 15:58 | 2.93
2020-02-15 | Worked on getting Travis to work | 10:18 | 17:58 | 7.66
2020-02-17 | Worked on getting Travis to work | 13:05 | 15:58 | 2.11
2020-02-17 | CS 4360 lecture | 12:00 | 12:50 | 0.83
2020-02-19 | Team meeting | 12:55 | 13:50 | 0.91
2020-02-19 | Made handout with overview of what has been accomplished so far with Last Seen app for group presentation | 14:00 | 15:55 | 1.91
2020-02-20 | Attempted once more to make Travis work with Github, efforts were still not successful | 22:15 | 23:48 | 1.55
2020-02-21 | Spent time reading up on potential solutions to making Travis work with Github and did not find a viable solution | 14:11 | 18:16 | 4.08
2020-02-24 | CS 4360 lecture | 12:00 | 13:00 | 1 | SPRINT 3
2020-02-24 | Team meeting | 13:05 | 15:10 | 2.08
2020-02-25 | Read and gained understanding about how to use bluetooth in Android from https://devofandroid.blogspot.com/2018/07/bluetooth-example.html | 12:01 | 17:30 | 5.48
2020-02-26 | CS 4360 lecture | 12:00 | 12:55 | 0.91
2020-02-26 | Team meeting | 12:59 | 13:58 | 0.98
2020-02-26 | Worked with Ron & Darey on enabling blue tooth with logging of blue tooth addresses on last seen hikers app | 14:00 | 15:59 | 1.98
2020-02-28 | Worked on enabling blue tooth with logging of blue tooth addresses on last seen hikers app with Darey | 13:05 | 19:21 | 6.26
2020-02-29 | Read book “Writing that Works” by Kenneth Roman | 9:01 | 15:32 | 6.51
2020-03-02 | CS 4360 lecture | 12:00 | 13:33 | 1.55
2020-03-02 | Trouble shooted last-seen checkpoints on Android Studio, which was not building properly after cloning, discovered the wrong branch was being used | 13:37 | 15:59 | 2.36
2020-03-03 | Worked on integrating blue tooth logging with Last Seen checkpoints | 14:33 | 18:00 | 3.45
2020-03-04 | CS 4360 lecture | 12:00 | 13:00 | 1
2020-03-04 | Helped Ron get his phone to sync with Android Studio | 13:02 | 15:45 | 2.71
2020-03-05 | Read the “Pragmatic Programmer” from chapters 1-5 | 10:25 | 16:11 | 5.76
2020-03-09 | CS 4360 lecture | 12:00 | 13:30 | 1.5
2020-03-11 | CS 4360 lecture | 12:00 | 13:25 | 1.41
2020-03-15 | Created filter page for Rescuer’s app | 8:00 | 15:30 | 7.5 | SPRINT 4
2020-03-16 | CS 4360 lecture | 12:00 | 13:15 | 1.25
2020-03-17 | Read the “Pragmatic Programmer” from chapters 6-8 | 12:20 | 18:47 | 6.45
2020-03-18 | CS 4360 lecture | 12:00 | 13:20 | 1.33
2020-03-19 | Read the clean agile book chapters 1-8 | 7:09 | 15:42 | 8.55
2020-03-26 | Wrote summaries of what all of the pages did in our rescuer app | 12:42 | 1:18 | 0.6
2020-03-30 | CS 4360 lecture | 12:00 | 13:00 | 1 | SPRINT 5
2020-03-30 | Team meeting | 13:00 | 13:30 | 0.5
2020-04-01 | CS 4360 lecture | 12:00 | 12:30 | 0.5
2020-04-01 | Paired programming with Darey & Ron on linking selection page on rescuers app to back end of database | 12:30 | 14:30 | 2
2020-04-03 | Worked on selection page that was referencing dummy data on the back end server | 10:01 | 16:03 | 6.02
2020-04-06 | CS 4360 lecture | 12:00 | 12:30 | 0.5
2020-04-06 | Paired programming with Darey on linking BlueTooth page on rescuers app to back end of database | 12:30 | 13:59 | 1.98
2020-04-08 | CS 4360 lecture | 12:00 | 12:30 | 0.5
2020-04-08 | Team meeting | 12:30 | 12:45 | 0.25
2020-04-09 | Worked on presentation for sprint | 19:03 | 22:18 | 3.25
2020-04-10 | Worked on presentation for sprint | 12:50 | 15:58 | 3.13
2020-04-13 | CS 4360 lecture | 12:00 | 13:30 | 1.5 | SPRINT 6
2020-04-13 | Sprint planning and covering 5 grading points at end of sprint PowerPoint | 13:30 | 15:00 | 1.5
2020-04-15 | CS 4360 lecture | 12:00 | 12:29 | 0.48
2020-04-15 | Worked with Darey on “Send Bluetooth request to checkpoints from rescuer application” and “Send reply from checkpoints to rescuer application” | 12:30 | 13:29 | 0.98
2020-04-15 | Examined how new Bluetooth beacon code interacts with rest of rescuer app | 13:29 | 3:30 | 2.02
2020-04-16 | Read Working effectively with legacy code chapters 1 – 12 | 11:00 | 18:30 | 7.5
2020-04-16 | Read Working effectively with legacy code chapters 13 – 25 | 10:32 | 17:46 | 7.23
2020-04-27 | Troubleshooted sending Bluetooth request to checkpoints from rescuer application and refactoring of Rescuer’s pages | 10:00 | 17:45 | 6.75
2020-04-29 | Worked with Darey on “Send Bluetooth request to checkpoints from rescuer application” and “Send reply from checkpoints to rescuer application” | 12:30 | 15:30 | 3
2020-05-04 | CS 4360 lecture | 12:00 | 13:00 | 1
2020-05-04 | Team meeting | 13:00 | 13:35 | 0.58
2020-05-06 | CS 4360 lecture | 12:00 | 12:30 | 0.5
2020-05-06 | Helped Darey put together overview of Trek Points application for final presentation | 12:30 | 13:50 | 1.33